## Project Summary
Integrate Agent into Monitoring — Phase 1
Start: May 25, 2026 ¦ End: June 5, 2026 ¦ Duration: 10 Days
Component | Current Status | Goals | Phase
Research + Code Generation (Day 1 — May 25 ✓ DONE) | Claude API studied; architecture drawn; full backend codebase generated: FastAPI, 8 tools, Conversation Agent, Explanation Agent, Teams Bot, HMAC | Foundation + code complete. All Python files syntax-verified. | ✓ Done
Backend Testing & Debug (Day 2 — May 26) | Code written & syntax-verified; not yet tested against real Prometheus | All 8 metric endpoints return real data; PromQL fixed to match actual labels; all errors debugged | In Progress
Teams Integration (Day 3 — May 27) | Incoming/Outgoing Webhook handler code ready; not yet connected to Teams | ngrok exposes service publicly; Outgoing Webhook @AKSBot replies in thread; Incoming Webhook receives daily report | Pending
Daily Report CronJob (Day 4 — May 28) | daily_report.py and cronjob.yaml written; not yet scheduled or triggered live | CronJob runs and sends formatted daily report to Teams channel; report content verified correct | Pending
Production Deploy (Day 5 — May 29) | Docker image not yet built; K8s manifests have placeholder image | Docker image built & pushed; Deployed to AKS monitoring namespace; All endpoints live; sign-off complete | Pending
Teams Hardening (Day 6 — June 1) | ngrok + webhooks tested; needs_clarification flow verified; HMAC validation confirmed | Full Teams regression pass: 5 questions + refusal answered; HMAC blocks invalid requests. | Pending
Daily Report (Day 7 — June 2) | daily_report.py + teams_sender.py written; not yet triggered live | Report triggered manually; Teams card peer-reviewed; content clear and actionable. | Pending
CronJob + Chat Endpoint (Day 8 — June 3) | cronjob.yaml written; POST /teams/chat ready; not yet scheduled | CronJob applied to K8s; /teams/chat endpoint verified; end-to-end daily report accepted. | Pending
Docker + Registry (Day 9 — June 4) | Dockerfile written; not yet built or pushed | Image builds clean; Docker Compose full stack healthy; image pushed to registry. | Pending
Production Deploy + Sign-off (Day 10 — June 5) | K8s manifests ready with placeholder image; not yet deployed to AKS | Deployed to AKS monitoring namespace; security audit passed (no secrets in logs); Phase 1 sign-off complete; docs updated. | Pending

## 10-Day Plan
Execution Plan — Integrate Agent into Monitoring (Phase 1) ¦ May 25–June 5, 2026
Complete all tasks each day before moving to the next.
# | Task Name | Description / Acceptance Criteria | Priority | Depends On | Status | Notes
Day 1 — May 25 ✓ DONE
GOAL: Research Claude API + Cowork platform + draw architecture + generate full backend codebase. All done in 1 day.
1.1 | Research Claude API & architecture | Study Anthropic API, models, tool use, system prompts. Draw Phase 1 architecture diagram: Prometheus → Metrics Service → 2 Claude Agents → Teams Write CLAUDE.md, ARCHITECTURE.md, PROJECT_GOALS.md. Outcome: architecture clear, scope defined. | 1 | – | Done ✓ | CLAUDE.md, ARCHITECTURE.md
1.2 | Generate full backend codebase | Generate all Python modules: config.py, source_registry.py, auth_helper.py, prometheus_client.py, ai_agent.py, teams_sender.py, daily_report.py, conversation_agent.py, tool_dispatcher.py, teams_bot.py, app.py Generate tools/: 8 metric tool modules. All files syntax-verified with py_compile. Outcome: 17 Python files, 0 syntax errors. | 1 | 1.1 | Done ✓ | 17 files, all OK
1.3 | Configure multi-source Prometheus + Teams Bot | Configure 3 Prometheus sources in source_registry.py: 1. Prometheus (AKS in-cluster, basic auth) 2. uat-monitor-workspace (Azure AD) 3. uat-monitor-workspace-prometheus (Managed Prometheus) Add POST /teams/webhook with HMAC-SHA256 validation. Write TEAMS_SETUP.md. Outcome: multi-source routing + Teams handler ready. | 1 | 1.2 | Done ✓ | TEAMS_SETUP.md written
Day 2 — May 26
GOAL: Install dependencies, start service, confirm /health and /sources pass, map real Prometheus metric names.
2.1 | Install dependencies & create .env | pip install -r requirements.txt Copy .env.example → .env, fill in: PROMETHEUS_SOURCES (real URL + credentials) ANTHROPIC_API_KEY (none for now) TEAMS_WEBHOOK_URL (can be dummy for now) Outcome: service starts with no import errors. | 1 | – | Done ✓
2.2 | Start FastAPI and run health checks | uvicorn metrics_service.app:app --reload Test: GET /health → {status: ok} GET /sources → 3 configured sources GET /docs → Swagger UI loads Outcome: service starts clean. | 1 | 2.1 | Done ✓
2.3 | Browse real Prometheus and map metric names | Open Prometheus UI → Graph tab. Find actual metric names and labels: node_cpu_seconds_total (labels: instance, mode) node_memory_MemAvailable_bytes kube_pod_container_status_restarts_total kube_pod_status_phase container_cpu_usage_seconds_total Note which metrics exist vs which are missing. Outcome: list of PromQL fixes needed. | 1 | 2.2 | Done ✓ | Record in notes
Day 3 — May 27
GOAL: Fix all PromQL to match real labels; all 8 metric endpoints return HTTP 200 with real data.
2.4 | Fix PromQL in tools/ to match real labels | Edit tools/*.py to use correct label names. Common fixes needed: - namespace label vs exported_namespace - instance vs node label for node metrics - container != '' filter for cAdvisor metrics Re-verify syntax: py_compile tools/*.py Outcome: all PromQL matches real Prometheus. | 1 | 2.3 | Pending
2.5 | Create Teams Incoming Webhook | In Teams channel → Manage Channel → Connectors → Incoming Webhook → Configure → Create. Name: 'AKS Metrics Assistant' Copy the webhook URL. Paste into TEAMS_WEBHOOK_URL in .env. Test: python3 -c 'from metrics_service.teams_sender import send_to_teams; send_to_teams("Hello from AKS Bot!", "Test")' Outcome: test message appears in Teams channel. | 1 | – | Pending
Day 4 — May 28
GOAL: Verify AI agents end-to-end; install ngrok; Teams Incoming Webhook connected and test message delivered.
2.6 | Test Conversation Agent + Explanation Agent | Test POST /chat with 5 questions: 1. 'Is the cluster healthy?' 2. 'Pod restarts in namespace default' 3. 'Node CPU last 6 hours' 4. 'Restart the failing pod' → expect refused 5. 'Unhealthy pods in monitoring' Verify: - Conversation Agent returns correct JSON status - Explanation Agent reply is plain English (no PromQL) - Refused questions get clear refusal message Outcome: both agents work end-to-end. | 1 | 2.5 | Not Started
3.1 | Install and start ngrok | Download ngrok: https://ngrok.com/download Run: ngrok http 8000 Copy the HTTPS forwarding URL: e.g. https://abc123.ngrok-free.app Verify: curl https://abc123.ngrok-free.app/health → {status: ok} Outcome: service publicly accessible via ngrok URL. | 1 | 2.7 | Done ✓
Day 5 — May 29
GOAL: Outgoing Webhook registered; @AKSBot replies correctly in Teams thread for all 5 test questions.
3.3 | Create Teams Outgoing Webhook | In Teams channel → Manage Channel → Apps tab → Create Outgoing Webhook Name: 'AKSBot' Callback URL: https://abc123.ngrok-free.app/teams/webhook Description: 'AKS Metrics Assistant Phase 1' Click Create → copy HMAC Security Token. Paste token into TEAMS_OUTGOING_WEBHOOK_SECRET in .env. Restart FastAPI service to reload .env. Outcome: Outgoing Webhook registered. | 1 | 3.1, 3.2 | Not Started | Token shown once only — copy immediately
3.4 | Test @AKSBot in Teams channel | Type in Teams channel: '@AKSBot is the cluster healthy?' Expect reply in thread within 15 seconds. Test 4 more questions: '@AKSBot show pod restarts in namespace default' '@AKSBot node CPU last 6 hours' '@AKSBot any unhealthy pods in monitoring?' '@AKSBot restart the pod' → expect refused reply Outcome: all 5 tests pass, replies appear in Teams thread. | 1 | 3.3 | Not Started
Day 6 — June 1
GOAL: Clarification flow works; HMAC rejects bad requests; full Teams regression test passes.
3.5 | Test needs_clarification flow | Type: '@AKSBot check api-service errors' (no namespace given) Expect Conversation Agent asks: 'Which namespace is api-service in?' Reply with: '@AKSBot prod' Expect: follow-up metric query runs. Outcome: clarification flow works in Teams. | 2 | 3.4 | Not Started
3.6 | Verify HMAC security | Send a POST request to /teams/webhook with a wrong Authorization header: curl -X POST https://.../teams/webhook \ -H 'Authorization: HMAC invalidsignature' \ -d '{"type":"message","text":"test"}' Expect: HTTP 401 Unauthorized. Outcome: HMAC validation confirmed working. | 1 | 3.3 | Not Started
6.1 | End-to-end Teams regression test | Re-run all 5 @AKSBot test questions + 1 refused question from scratch on a clean ngrok session. Record pass/fail for each in Notes. Outcome: 5/5 questions answered + 1/1 refusal confirmed. | 1 | 3.6 | Not Started
Day 7 — June 2
GOAL: Daily report triggers, appears in Teams, content is readable and approved by one team member.
4.1 | Trigger daily report manually | Call: POST /daily-report curl -X POST http://localhost:8000/daily-report Verify a formatted card appears in Teams channel. Check content includes: - Overall status (Healthy / Warning / Critical) - Node CPU + memory summary - Pod restart counts - Unhealthy pod count - Warnings section (if any) - Suggested investigation (if needed) Outcome: report appears in Teams, content is readable. | 1 | 3.2 | Not Started
4.2 | Improve daily report content and format | If report is too verbose or missing key data: Edit generate_daily_report_text() in ai_agent.py Adjust the daily_prompt to focus on key metrics Ensure Teams message card is under 28,000 chars If metric data is thin: Edit collect_metrics() in daily_report.py Add more namespaces to daily_report_namespaces Outcome: report is concise, actionable, Teams-readable. | 2 | 4.1 | Not Started
7.1 | Peer review daily report | Ask one team member to read the Teams card and confirm it is clear, actionable, and under 28 kB. Incorporate any feedback before Day 8. Outcome: peer approval recorded. | 2 | 4.2 | Not Started
Day 8 — June 3
GOAL: CronJob scheduled; /teams/chat endpoint verified; end-to-end daily report accepted.
4.3 | Apply CronJob to Kubernetes | kubectl apply -f k8s/cronjob.yaml -n monitoring Verify schedule in cronjob.yaml (e.g. '0 8 * * 1-5' = 8AM weekdays). Manually trigger one-off job: kubectl create job daily-report-test \ --from=cronjob/aks-daily-report -n monitoring Check job completes: kubectl get jobs -n monitoring Verify Teams receives the triggered report. Outcome: CronJob scheduled and one-off trigger confirmed. | 1 | 4.1 | Not Started | Requires AKS access
4.4 | Test POST /teams/chat (Power Automate path) | Test the second chat endpoint (non-webhook path): curl -X POST http://localhost:8000/teams/chat \ -H 'Content-Type: application/json' \ -d '{"message": "show pod restarts in default", "user": "DevOps"}' Verify: response.status == 'answered' reply is plain English message sent to Teams Incoming Webhook Outcome: /teams/chat endpoint verified. | 2 | 3.2 | Not Started
4.5 | End-to-end daily report review | Run a full daily report review: Trigger report → check Teams card Verify each metric section has real data Check no placeholder text or errors Confirm report arrives within 30 seconds Ask team member to review Teams message readability Outcome: report approved for production. | 1 | 4.1–4.3 | Not Started
Day 9 — June 4
GOAL: Docker image builds, runs cleanly in Compose alongside Prometheus stack, pushed to registry.
5.1 | Build and test Docker image | docker build -t aks-metrics-service:latest . Fix any build errors (missing deps, wrong paths). docker run --env-file .env -p 8000:8000 aks-metrics-service:latest Test inside container: GET /health, GET /sources, GET /metrics/cluster-health Outcome: image builds and runs cleanly. | 1 | 2.7 | Not Started
5.2 | Add to Docker Compose and test full stack | Add aks-metrics-service to monitoring/docker-compose.yaml. Set PROMETHEUS_SOURCES URL to: http://prometheus:9090 (Docker DNS, not localhost) docker compose up -d Verify all 5 containers healthy: prometheus, grafana, alertmanager, prometheus-msteams, aks-metrics-service Outcome: full stack runs in Docker Compose. | 1 | 5.1 | Not Started
5.3 | Push image to container registry | docker tag aks-metrics-service:latest \ <your-registry>/aks-metrics-service:v1.0.0 docker push <your-registry>/aks-metrics-service:v1.0.0 Options: Azure Container Registry (recommended) or Docker Hub. Note the full image path for deployment.yaml. Outcome: image available in registry. | 1 | 5.2 | Not Started
Day 10 — June 5
GOAL: Production deploy live; security audit clean; Phase 1 sign-off complete; documentation updated.
5.4 | Deploy to AKS production namespace | kubectl create secret generic aks-metrics-assistant-secrets \ --from-env-file=.env -n monitoring Update k8s/deployment.yaml with real image path. kubectl apply -f k8s/ -n monitoring Verify pod running: kubectl get pods -n monitoring kubectl logs -l app=aks-metrics-service -n monitoring Outcome: pod Running, /health returns ok from inside AKS. | 1 | 5.3 | Not Started | Never commit .env
5.5 | Security audit — no secrets in logs | Trigger errors inside AKS: kubectl exec ... -- curl 'localhost:8000/metrics/pod-restarts?namespace=../etc' kubectl exec ... -- curl 'localhost:8000/metrics/node-cpu?range=9999d' kubectl logs -l app=aks-metrics-service -n monitoring Grep for: password, secret, token, api_key, client_secret. Expect: ZERO credential strings in any log line. Outcome: secrets confirmed not in logs. | 1 | 5.4 | Not Started
5.6 | Test all endpoints live in AKS | kubectl port-forward svc/aks-metrics-service 8000:8000 -n monitoring Test all 8 metric endpoints + /health + /sources. Test Teams chat via @AKSBot with real AKS data. Trigger daily report from production. Outcome: 100% of endpoints pass in production. | 1 | 5.4 | Not Started
5.7 | Phase 1 sign-off checklist | Confirm all acceptance criteria: ✓ Daily report arrives in Teams (scheduled + manual) ✓ @AKSBot answers metric questions in Teams thread ✓ Refusal of all remediation requests ✓ No secrets in logs (confirmed 5.5) ✓ All 8 metric tools return real AKS data ✓ HMAC signature validated on Outgoing Webhook ✓ Azure AD auth working for UAT Prometheus ✓ Docker image in registry, K8s deployed Outcome: Phase 1 complete — ready for Phase 2. | 1 | 5.1–5.6 | Not Started
10.1 | Update final documentation | Update README.md, ARCHITECTURE.md, and PROJECT_GOALS.md to reflect Phase 1 completion status. Confirm CLAUDE.md scope is still accurate. Outcome: all docs reflect production-live state. | 1 | 5.7 | Not Started